## Competences-Matrix
Project services; cost engineering, cost estimation, planning and scheduling, risk management
[10 empty] | Participant | Examination by
Education Domains Learning Outcomes | Knowledge layer The cost engineer should know and understand: | Skill Layer The cost engineer is able to apply knowledge: | Competence Layer (Leadership Skills) To cost engineer is able to execute and apply in context: | Course Subjects (Indicative) | [5 empty] | Demonstrate basic knowledge before training | Answering theoretical questions in given time frame | Problem solving / Calculation in given time frame | Practical Case study | DACE Case study | Paper
A. Project Environment and Project Services Engineer |  |  |  | A1 | A2 | A3
Organizations | Typical owner/ engineer/ contractor/ consultancy organization | Organizational Breakdown Structure |  | Introduction & Structure of the Course | Applied Statistics | Business Analytics
Position & Role of Project Services Engineer in different organization models
Line vs. matrix organizations
Company organization vs. project organization
Stakeholders vs. project organization
Relation project organization vs. (longer term) inspection / maintenance and operational department
Multi project | Portfolio management | [11 empty] | x
Investment decision criteria | Criteria for investment selection including IRR, NPV, Break even, sunk cost | Calculate and evaluate different investment options | [10 empty] | x
| Techniques of IRR, NPV, break even, sunk cost | [11 empty] | x
Value | Maximization of value, including Value Management, Lean, Kaizan etc. | [10 empty] | x | x
Typical business model of owner/ engineer/ contractor/ consultant
| Techniques for maximization of value and cost optimization, including Value Management, Design to cost and Life Cycle Costing | [10 empty] | x | x
Financing | Methods of project financing | [11 empty] | x
B. Project Management |  |  |  | B1a | B1b | B2 | B3 | B4
Project Management | Project team, team dynamics | Own profile in team (Meyers Briggs or other) |  | Project Management General | Project Management General | Multi Project Environment | Contract & Claim Management | Risk Management |  |  | x
Stakeholders
| Cost drivers | Explain the relations between all project elements and costs
Interfaces
Change control
Project phasing
Opportunity vs, project concept
Stage gate models
Project life cycle concepts
| Project Execution Plan (PEP); Project Implementation Plan (PIP) | Develop PEP | [8 empty] | x
Quality assurance / control (QA/QC)
Assurance
Lessons learned
Project Management | General principles of project management including project plan, project controls | [9 empty] | x
Contracting models | Alliance, consortium, management contracting, contract management (for and on behalf), subcontract, EPCMO, EPCM,EPC,EP(CM)
Single source, competition
Lump sum, unit rate, reimbursable, time & material, provisional sum, prime cost
Contract Management | Contract and Claim management | [9 empty] | x
HSSE |  | Prepare management of HSSE risk
Risk Management | Risk management in projects | Create and maintain a risk register | [8 empty] | x |  |  | x
Risk assessment | Continuous risk | Calculate & analyse risks in time | The background of scheduling, Monte Carlo simulation and statistics
Discrete risk
Probability of events
C. Estimating |  |  |  | C1 | C2 | C3 | C4 | C5 | C6
Estimate | Key purpose |  |  | Estimating Methods | Detailed Estimating | Estimating Engineering Costs | Indirect Costs | Accuracy & Contingency | Parametric Estimating |  | x
Application
| Pricing | Database / suppliers / subcontractors | Evaluation of quotations of suppliers/ subcontractors
Construction methods
| Cost database | Create a cost database | Improve a cost database
| Commercial model |  | Commercial models vs. risk vs. costs
Direct cost (labour, equipment, bulk materials, construction equipment)
Indirects (D/E, CM, transportation, temporarily facilities)
Allowances
Contingency
| Relation risk and schedule | Calculate & analyse risks in money | The background of scheduling, Monte Carlo simulation and statistics
Phasing; mid point of expenditure
Escalation
| Accuracy | Apply statistical techniques | The relation between project life cycle (phasing) and the different levels of estimate accuracy
Probability
Review and assurance
Benchmarking
Estimating methods | Different estimating techniques; quantitative estimate, factor estimate, parametric estimate, scaling (up and down), location factors, escalation | Create a quantities' estimate | [8 empty] | x
|  | Create a factor estimate | [11 empty] | x
|  | Create a parametric estimate | [9 empty] | x
Provide up and down scaling
Define specific regional cost dependencies (location factors)
Define escalation
Different techniques for different disciplines, mechanical, piping, electrical, infrastructure, civils, building and indirect costs
Estimate plan | Elements of a basis of estimate |  | Write a basis of estimate | [7 empty] | x |  |  | x
Estimate validation | Scoping development | Scoping validation completeness
| Method and elements | Project evaluation | Validate a multi disciplinary investment estimate by linking scope, time, risk and organization into a capex estimate. | [7 empty] | x |  |  | x
Estimate as part of controls |  | The relation between estimate, schedule, risk and contingency | [11 empty] | x
D. Scheduling |  |  |  | D1 | D2 | D3 | D4 | D5
Schedule | Key purpose |  |  | Scheduling Techniques | Resources en Cost (Scheduling) | Advanced Planning & Constraints | Schedule Risks | Schedule Risks Simulations |  |  | x
Application
Deterministic baseline
The elements of a basis of scheduling
Productivity
| Project phasing | [9 empty] | x
| Schedule information database | How to create a schedule information database
Milestones
| Activities, activity relations, (early) start and finish | The relation between project life cycle (phasing) and the different detail levels of scheduling | Create a comprehensive schedule, that is in line with the entire project control plan
Define a project schedule, with applicable detail level for particular project stage, maximum level 3.
Critical path
Slack (free) float
| Relatioin risk and schedule | Calculate & analyse risks in time | The background of scheduling, Monte Carlo simulation and statistics
| Progress | Techniques for measuring progress
| Resource loading | Develop a resource plan
Calendars
| Multiparty schedule | Techniques for integration of owner and contractor schedules | [8 empty] | x
Review and assurance
Benchmarking
Schedule preparation | Different scheduling techniques and how to built a (network) schedule | [9 empty] | x
| Different techniques for presenting schedule information | [12 empty] | x
EVC | Earned Value Analysis (cost and hours) | Perform an Earned Value Analysis | [11 empty] | x
Cash flow | The relation between time and money, cash flow plan | Define a cash flow plan based on budget and project funding | [8 empty] | x |  |  | x
Schedule basis plan | Integrated plan and controls |  | Write a basis of schedule | [10 empty] | x
Schedule validation | Scoping development | Scoping validation completeness
| The elements of a schedule validation |  | Validate a level 3 schedule | [10 empty] | x
Schedule as part of controls | Manage schedule change | The relation between estimate, schedule, risk and contingency | [11 empty] | x
E. Cost Management and Controls |  |  |  | E1 | E2 | E3 | E4 | E5
Cost management | Key purpose |  |  | Cost Control Introduction | Cost Accounting & Change Management | Cost Analysis & Forecasting | Cost Coding & Indexation | Cost Accounting |  |  | x | x | x | x | x
| Procedure | Cost management procedure apply
| Cost baseline and management | Set up framework
Budget
| Cost control / accounting | Definition of project procedures to organize cost control
Commitment, non-committed
Actual, Value Of Work Done (VOWD)
| Estimate at Completion (EAC) | The elements of a estimate at completion analysis | Perform a reliable estimate at completion for a project
Contingency rundown
Risk depletion
Budget shift
Management of Change
Cash flow & cash management
Change control
Progress measurement
Re-base lining
Capitalization and depreciation
OPEX / CAPEX
Cost breakdown (cost place, cost sorts) | Principles of Work Breakdown Structure (WBS) and the relation with schedule, budget, organization |  | Create a WBS for a project , that will form the back bone of the project controls (time, money, organization / contracting.
|  |  | Maintain a WBS in different stages of a project, adapting all project control elements | [7 empty] | x
| Cost Breakdown Structure (CBS) | [12 empty] | x
| Activity Breakdown | [12 empty] | x
Project Control Plan |  | Provide a cost management report | Write a project control plan, including time, money, risk, organization and scope development | [10 empty] | x
Cost management code system | To maintain the relation between budget and cost control by creating structure and procedures
Project close out | Project close out and evaluation | Create and maintain a cost report | Cost management evaluation | [7 empty] | x
| Closing the loop (lessons learned) | gathering feed back
F. Communication & Soft skills |  |  |  | F1 | F2
Communication | Roles of Project Services Engineer within a project team (incl. collaboration, advisory skills, identification of cost reduction/value improvement/margin improvement opportunities etc.) |  | Influence / persuade outside direct responsibility | Reporting Skills | Presentation Skills
Communication Report | The elements of a successful report | Report the requested information in a convincing way
Presentation | The elements of a successful presentation including presentation techniques, support of power point | Present a cost engineering topic in a convincing way | [11 empty] | x | x
Provide a report to a stakeholder
Project reviews with principal (client) and own organisation (internal project team)
G. Application and Innovation (CASE / PAPER) |  |  |  | G1 | G2 | G3 | G4
Reflect and learn |  |  | To select and analyse a part of theory | Case Study I | Case Study II | Case Study III | Paper | [7 empty] | x
|  |  | Reflect on experience | [11 empty] | x
Analysis and solve problems
Demonstrate creativity and innovation
|  |  | Practice on other disciplines to gain new insights; aiming to improve the Project Services Discipline. | [11 empty] | x

## Course-Subjects
Project services; cost engineering, cost estimation, planning and scheduling, risk management
Education Domains | Objectives / Learning Outcomes | Content | Literature | Curriculum Study Load
A. Project Environment and Project Services Engineer |  |  |  | Total Workload: ~ 50 hrs | Online: | F2F: 6 x 2hr
A1. Introduction & Structure of the Course | Participants will be given an overview of the entire course, including the organization, and the relationship with DACE | DACE organization
Structure of the Course
A2. Applied Statistics | Successful implementation of the presented statistical techniques and methods | Statistics plays an important role in the activities of a cost engineer and is one of the areas of expertise where a cost engineer can truly make the difference within a project team
Final goal of this module is to teach the future cost engineer several statistical techniques and methods useful in his daily work. The main focus will lie on exercises, the amount of theory will be limited to what is required to understand and successfully implement the presented statistical techniques and methods
Amongst others the presented techniques will include statistical analysis of available information and predictions based on simulation techniques (more specifically Monte Carlo simulations)
Given the importance for a cost engineer of spreadsheet software such as Microsoft Excel and given its suitability as a tool for both statistical analysis as for reporting, most exercises will be made using this software
A3. Business Analytics | Paricipants will learn to understand Investment Decision Criteria in Companies | Company perspective, terminology like IRR, NPV, Break even, and sunk cost, will be explained.
Calculate and evaluate different investment options
B. Project Management |  |  |  | Total Workload: ~ 75 hrs | Online: | F2F: 8 x 2hr
B1a. Project Management General | Understand the history and necessity of project managemet | Introduction to project management | Book "Management of engineering Projects"
| Describe the definition of a project and its distinctive features | History of project management
| Understand the project enviroment | Definition of project management
| Identify the various phases of the project life-cycle | Project-based execution
Comparison of the various project management methods
Project environment
Project life-cycle
B1b. Project Management General | Understand the importance of structured project communication | Definition of project communication
| Develop an internal and external communication plan | Develop internal/external communication plan
| Understand concepts of stakeholder management | State of the art systems for team communication
| Perform a force field analysis | Progress reporting and analyses
| Understand “safety first” philosophy | Project administration
Alignment and decision-making
Project context and Stakeholder management
Force field analysis
HSE management
B2. Multi Project Environment | Participants will learn how to work in a complex project environment, how to deal with priorities, conflicting project objectives, and different stakeholders. This module should provide an understanding of the Project Portfolio Management. | Difference between Projects and Programmes
Competition for scarce resources, relationship with and impact on schedule
Setup of Project Management Office (PMO)
Understanding of Portfolio Management, value for a company
B3. Contract & Claim Management | Participants will learn the importance of a good Contract in a project. Different Contract Types will be explained. Also sub-contracting strategies will be treated in this subject. The importance of a good project administration will be explained. | Project Contract - structure, terms & conditions, subcontracts, sourcing plan, liabilities
Changes and Transfer of Risk
| Participants will learn about all aspects of Claims Management | Project filing, electronic archives, potential claims
Claims related to delays; Claims related to Scope Changes; Inefficiency Claims
B4. Risk Management | Risk Management function in a Project Team | Risk Management in a Project, risk ownership, risk register, risk workshops with project team, risks versus trends
| Inventory of Risks, how to phrase and how to deal with risks | Framing of Risks and Opportunities - Importance of Language
| Risk Mitigation, consequences, monitoring of risks | Quantification of Risks. Foundation for Cost & Schedule Risk Assessment, Cost Contingency Assessment, Float in Schedule
C. Estimating |  |  |  | Total Workload: ~ 150 hrs | Online: | F2F: 12 x 2hr
C1. Estimating Methods | Participants will learn what factors are applicable in different situations | Factor Estimating
| Participant will learn to work with these factors | Capex Estimate for investment decision of chemical plant
| Participants will learn what the constraints and risks are | Life-cycle of Greenfield Construction Project
Global Estimating Methods in early project phases
Detailed Estimating methods in later project phases
Estimating based on actual cost of comparable project, that has been realized
Up- and Down-scaling factors
Location Factors (global)
Benchmarks and Metrics
C2. Detailed Estimating | Understanding the structure of a detailed Cost Estimate, and knowing when in the life-cylce of a project a detailed Cost Estimate will be typically required | Detailed Cost Estimating of Maintenance Projects, focussing on duration of installation and de-installation
Detailed Cost Estimating of New Greenfield Projects, focussing on material cost and cost of labour
Norm Hours
Labour Rates
Sources for Material Cost
C3. Estimating Engineering Costs | The participants will learn about Engineering costs, covering Basic (Front-end) Engineering as well as Detailed Engineering. The life-cycle of a project will be followed to explain first the global, and later the more detailed methods of estimating Engineering costs. | Scope Definition
Unit Rates
Accuracy
Presentation of the Cost Estimate
C4. Indirect Cost | The participants will learn (the different) definitions of direct and indirect costs, and understand how to estimate the various elements that contribute to the indirects | Indirect Costs Contractor versus Owner
Construction Supervision
(Construction) Site Facilities
Commissioning & Start-up
Insurance
Overhead
Market Escalation & Inflation (including Currencies)
Cost Indexation
Profits (and Risk Premiums)
C5. Accuracy & Contingency | The participant should understand the factors that influence the accuracy of a Cost Estimate. It should be understood what is the difference between accuracy and reliability of a cost estimate | Accuracy in general, and in relationship with Cost Estimates; Factors that influence accuracy of an Estimate
| The participants should understand what the Contingency in a Cost Estimate is (for). Based on the Risk Profile of a project, the participants should be capable of making a transparent and consistent contingency assessment. | Contingency: What is it, what it isn't
Methods for defining contingency
Relationship Risk Management & Contingency
C6. Parametric Estimating | The course member should be able to: • Understand Parametric Analysis (PA) as part of cost estimating process. • Know where and when to apply and not to apply PA and able to conduct a PA • Able to develop a Cost Estimating Relationship
D. Scheduling |  |  |  | Total Workload: ~ 80 hrs | Online: | F2F: 8 x 2hr
D1. Scheduling Techniques | Participants will learn to understand the importance of planning in an organization as well as in a project | Planning Techniques - general | Book "Burke"
| Different Planning Techniques will be covered | Identify Activities for a Planning
| Participants will learn to setup a Network Planning, and should understand the basic rules of scheduling calculations | Basic Rules of Scheduling, including relationships
Presentation of Planning Information (Reporting)
D2. Resources and Cost (Scheduling) | Participants will learn techniques to do planning calculations, and how to develop a cash flow curve. | Resource Loaded Schedule, i.e. incorporation of capacity and costs in Planning
Develop cash flow curve
| They will learn how to incorporate actual progress in the Planning | Manual calculations of a network planning
| Participants will learn how to interpret the development of cash flow in various phases of a project | Updating the Planning
D3. Advanced Planning & Constraints | Participants will learn how to schedule with date and capacity constraints | Scheduling with Calendars, Date constraints
Leveling, i.e. resolving capacity conflicts
D4. Schedule Risks | Participants will get insight in application of various risk analysis methods in relation to planning | Basic principles of risk analysis and planning
RISMAN Method
Quantitative Risk simulation (Monte Carlo)
D5. Schedule Risks Simulations | Participants will apply Monte Carlo simulations on planning | Monte Carlo simulation, analysis of simulation results
They will learn how to include Float
E. Cost Management and Controls |  |  |  | Total Workload: ~ 125 hrs | Online: | F2F: 10 x 2hr
E1. Cost Control Introduction | Gain understanding of importance of Cost Control, and learn who will benefit | Introduction to Cost Control
Views of Owner/Operator versus Contractor
Project Cost Management during Front End Loading
Stakeholders in execution of project
Contract types
Project Controls loop
E2. Cost Accounting & Change Management | Participants will learn how to setup a Cost Report | Terminology in Cost Report
From Cost Estimate to Budget
Cost Coding
Commitments & Expenditure
Cost Developments & Changes
Control Estimate
Contingency Rundown
S-curve
E3. Cost Analysis & Forecasting | Participants will learn tools to understand the physical progress of a project. | Progress measurement of Engineering, Procurement and Construction
| With the combination of Finance Data and Physical Progress, participants will learn how to predict total expected project cost | Estimate to Complete
Indicated Total Cost
E4. Cost Coding | Cost Coding: Requirements, usage, advantages | Barcoding
Project Cost Coding System
Cost Coding System requirements
Cost Coding in relation to Cost Estimating and Cost Control
E5. Cost Accounting | Participants will learn relevant interfaces between Cost Engineering and Accounting. They will understand how Cost Data is used for Financial Reports and Results in a Company | Management Accounting
Break-even analysis; Make and Buy decisions
Performance Management (Financial Ratio Analysis)
F. Communication & Soft skills |  |  |  | Total Workload: ~ 50 hrs | Online: | F2F: 4 x 2hr
F1. Reporting Skills |  |  | Report writing for readers with little time (Elling et al., 2012)
F2. Presentation Skills
G. Application and Innovation |  |  |  | Total Workload: ~ 200 hrs | Online: | F2F: 10 x 2hr
G1. Case Study I
G2. Case Study II
G3. Case Study III
G4. Paper
X. Special Applications |  |  |  | Total Workload: 20 hrs | Online: | F2F: 4 x 2hr
X1. Value Engineering
X2. Cost Estimating Civil |  | e.g. Examples Buildings/Wind Turbines
X3. Dutch versus International Market |  | Location Factor; World Table; Modularization
X4. Closing the Loop |  | Data feedback loop; Business Cases
Possible other subjects to be considered
Detailed Cost Estimating of Process Automation
Detailed Cost Estimating of Electrical & Instrumentation scope
Dutch versus International Market
Detailed Cost Estimating of Piping scope
Dredging
Cost Estimating in Manufacturing Industries

## Overall-Planning
Project Planning CCE 2.0 |  | Start date (of week) | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 1 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29
|  | Finish date (of week) | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4
|  | Weeknr | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5
[20 empty] | 2017 | [51 empty] | 2018
|  | Who? | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Development of Course Content
| Setup and test Online Course Environment | Logistics Coordinator | [8 empty] | Setup online environment
| Project Mgt - Course Materials | Hans Bakker | Struct/Layout |  |  |  | Align |  | Draft Materials | [5 empty] | Final
| Scheduling - Course Materials | Marcel Pieters | Struct/Layout |  | Align |  | Translations |  |  |  | Final
| Estimating - Course Materials | CEC | Struct/Layout |  |  |  | Align |  | Draft Materials | [5 empty] | Final
| Cost Control - Course Materials | T&T | Struct/Layout |  |  |  | Align |  | Draft Materials | [5 empty] | Final
| Select Optional Course Subjects | Edward
Other Subjects - Develop Course Structure and Layout, identify development needs
Other Subjects - Develop all Course Materials
Course 2017 - Online Work / Face-to-Face / Exams
Introduction
Communication & Soft Skills
| Scheduling | Marcel Pieters
| Project management | Hans Bakker
| Cost Estimating | CEC
| Cost Management & Controls | T&T
Other Subjects
CASE STUDY
PAPER | bar: Feb to Mar
Holidays in Netherlands
Online Study
Face-to-Face Lessons
Study for Exams
Exams

## Curriculum-F2F-Schedule
DACE "Certified Cost Engineer" 2017 - FACE-to-FACE Schedule Curriculum
This is schedule showing FACE-to-FACE (F2F) parts of the Course.
| Hotel Houten |  |  | ENGIE / Fabricom Dordrecht |  |  |  | Shell Rijswijk |  |  | TBD |  |  | Boskalis Papendrecht |  |  | DACE
| February 2017 |  |  | April 2017 |  |  |  | June 2017 |  |  | September 2017 |  |  | November 2017 |  |  | January 2018
| Block 1 | "Introduction" |  | Block 2 | "Conceptual" |  |  | Block 3 | "Preparation" |  | Block 4 | "Execution" |  | Block 5 | "Project Completion" |  | Block 6 | "Evaluation"
| 2017-02-14 | 2017-02-15 | 2017-02-16 | 2017-04-11 | 2017-04-12 | 2017-04-13 |  | 2017-06-20 | 2017-06-21 | 2017-06-22 | 2017-09-19 | 2017-09-20 | 2017-09-21 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2018-01-16 | 2018-01-17 | 2018-01-18
08:15 - 10:15 | A1 | D1 | G1 | B1a | D3 | C1 |  | EXAM D | C3 (Risk) | B2 | EXAM B | F2a | C5 | EXAM C | E2 | E4 | EXAM E | X2 | G3'
10:30 - 12:30 |  |  | A2 |  |  |  |  | G1' |  | B3 | G2' | F2b |  |  |  |  | X1 | X3
13:30 - 15:30 | F1 | D2 |  | B1b | Factory Tour | C2 |  |  | C4 | B4 |  | E1 | C6 | G3 | E3 | E5 | A3 | X4
15:45 - 17:45 |  |  | Guest Speaker |  | D4 |  |  | G2 |  |  | G4 |  |  | Guest Speaker
Course Dinner
| Legend: | Education Domain: | [6 empty] | Selected Partner: |  | Potential Alternative:
|  | A1. Project Environment and Project Services Engineer |  |  |  |  | F2F: 2 x 2hr |  | DACE - Edward Rademaker
|  | A2. Applied Statistics |  |  |  |  | F2F: 2 x 2hr |  | DACE - Witek ten Hove (HAN) |  | Carlo Holvoet / SIG-PRA
|  | A3. Business Analytics |  |  |  |  | F2F: 2 x 2hr |  | DACE - Friesland-Campina
|  | B. Project Management |  |  |  |  | F2F: 8 x 2hr |  | Hans Bakker |  | Fluor - Marco Eykelenboom
|  | C. Estimating |  |  |  |  | F2F: 12 x 2hr |  | Cost Engineering Consultancy (CEC) |  | Turner & Townsend (T&T)
|  | D. Scheduling |  |  |  |  | F2F: 8 x 2hr |  | MPPL - Marcel Pieters
|  | E. Cost Management and Controls |  |  |  |  | F2F: 10 x 2hr |  | Turner & Townsend (T&T) |  | Cost Engineering Consultancy (CEC)
|  | F. Communication & Soft skills |  |  |  |  | F2F: 4 x 2hr |  | DACE - Marc Draaijer |  | DACE
|  | G1/G2/G3. Application and Innovation (CASE) |  |  |  |  | F2F: 10 x 2hr |  | DACE - Boudewijn Smolders |  | DACE
|  | G4. Application and Innovation (PAPER) |  |  |  |  | F2F: 1 x 2hr |  | DACE - Carlo Holvoet |  | DACE
|  | Exams |  |  |  |  | F2F: 4 x 2hr
|  | X. Special Applications |  |  |  |  | F2F: 4 x 2hr
Still open, to be decided